## Cover
Technology Group International
Software Selection Checklist and Project Timing Chart
Software Selection Check list
Software Selection Project Timeline
Software Selection Gantt Chart
Copyright 2004 Technology Group Intertnational, Ltd.
All Rights Reserved

## Checklist & Timing Chart
Software Selection Project Timing Chart & Checklist
Software Selection Project Task | Estimated Time to Complete | Start Date | Due Date | Task Owner | Status
Phase 1 - Research and Planning
Obtain Initial Executive Support | [5 empty] | In Process
Form a Steering Committee | [5 empty] | Late
Interview Corporate Executives and Senior Management | [5 empty] | Complete
a. Review Key Business Initiatives
b. Long Term Goals
Interview Information Technology (IT) and Operations Managers
Identify Internal and External Stakeholders
Define Project Objectives and Identify Project Constraints
Perform a High Level Needs or Requirements Analysis
Evaluate Existing System Performance
Interview Functional Departments Managers and Key Users
Develop a Strategic Systems Plan
Develop a Detailed Project Plan
a. Define Project Structure
b. Define Project Scope
c. Identify Project Phases and Tasks
d. Identify Resource Requirements
Prepare a Business Case
a. Prepare a Project Budget
b. Define Tangible and Intangible Project Benefits
c. Calculate Potential ROI
Present Business Case to Executive Staff
a. Obtain Executive Level Support
b. Obtain Approval of Project Plan & Resources
c. Obtain Budget Approval
Assign an Executive Champion
Phase 2 - Requirements Identification and Proposal Preparation
Inform the Organization of the Project
a. Inform Department Managers of Project and Resource Needs
b. Inform General Employees of Systems Project
Form a Project Team
Educate Team on Project Plan
Establish Project Controls
Perform Requirements Definition Analysis
a. Review Existing Business Processes
b. Interview Functional Areas
c. Prepare for the Definition of Requirements
d. Identify Hot Buttons (Must Have Items)
e. Prioritize Requirements
f. Review Completed Requirements with Project Team
Research and Identify Long List of Potential Suppliers (15 – 25)
Create a Draft Request for Proposal (RFP)
Phase 3 - Supplier Evaluation
Gather Information on Potential Suppliers
Conduct Supplier Interviews with Long List of ERP Software Suppliers
a. Define Supplier Questionnaire and Initial Selection Criteria
b. Perform Verbal Interviews or Issue Formal RFI
Reduce Initial Long List of ERP Software Suppliers (10 – 15)
Conduct Remote ERP Software Demonstrations for Long List of Suppliers
Reduce Suppliers to Short List of Candidates (5 – 7)
Finalize RFP and Submit to Supplier Short List
Initially Review Supplier RFP Responses
Reduce Potential Supplier List if Necessary
Perform On-Site ERP Software Demonstrations with Supplier Short List
a. Develop Detailed Demonstration Script
b. Provide Demonstration Script to Suppliers for Demo Preparation
c. Perform On-Site Individual Supplier Demonstrations
d. Score and Document the Team’s Assessment of Suppliers
Phase 4 - Supplier Selection
Further Review and Evaluate RFP Responses
Further Review and Evaluate On-Site Demonstrations
Calculate Overall Weighted Score Analysis for Suppliers
Reduce Short List to Two Top ERP Suppliers
Conduct On-site Reference Check for Top Two Suppliers
Select Supplier of Choice
Notify Suppliers of Decision
Negotiate Contract
Phase 5 - Implementation
Form Joint Project Team with Supplier
Define Project Charter
Order System Hardware
Order Third Party System Software
Install Network Hardware
Install Database and Required Third party System Software
Install ERP Software
Perform Initial User Training
Perform Initial Technical Training
Validate ERP Software
Review Current Processes and Create Work Flow Diagrams
Perform Value Stream Analysis for Required Process Improvements
Define System Data
a. Populate Base Tables in the Software
b. Cleanse Existing Data for Conversion to New ERP Software
c. Migrate Cleansed Data to New ERP System
Define System Reports
a. Review Reports in Existing System
b. Review Standard Reports in New System
c. Prepare Customized Report Listing
d. Create Customized Reports
Define Modifications
a. Review Value Stream Analysis and Work Flows
b. Identify Required Modifications to Existing Work Flows
c. Request and Review Supplier Quotes for Modifications
d. Authorize Necessary Modifications
e. Test Completed Modifications
Develop Integrated Test Plan
Document New Policies and Procedures for Users
Test System with Dual Path Approach if Necessary
Finalize System Security
Train Remaining System Users
Train Remaining Technical Personnel
Pilot System (Execution of Integrated Test Plan)
Benchmark System Performance at Pilot
System Sign Off
Implement Remaining Locations
Perform Post Implementation Review
Perform Additional Training if Necessary
Perform Additional Modifications if Necessary